## Iteration 1
Plan - Iteration 1
Activity Nr | Activity Description | Assigned Team Member(s) | Hours dedicated | Task Start Date | Task Deadline
1 | Application structuring - discussion | Team | 6:00 | 2018-03-09 | 2018-03-16
2 | Update URS | Ivelin & Vasil | 6:00 | 2018-03-09 | 2018-03-16
3 | Concept version of Design document | Marina & Lyubomir | 6:00 | 2018-03-09 | 2018-03-16
4 | Concept version of Test Plan (Report) | Joseph & Emil | 6:00 | 2018-03-09 | 2018-03-16
5 | Concept version of Plan for Iteration 2 | Ivelin & Vasil | 2:00 | 2018-03-16 | 2018-03-23
6 | Update Design document | Marina & Lyubomir | 2:00 | 2018-03-16 | 2018-03-23
7 | Update Test Plan | Joseph & Emil | 2:00 | 2018-03-16 | 2018-03-23
8 | Reseacrch and Introduction to WPF and CSV | Team | 8:00 | 2018-03-09 | 2018-03-23
9 | Import a CSV file with data | Emil | 6:00 | 2018-03-16 | 2018-03-29
10 | Parse data from the imported file | Joseph | 6:00 | 2018-03-16 | 2018-03-29
11 | Pass the imported data to the pie chart | Ivelin | 6:00 | 2018-03-16 | 2018-03-29
12 | Create standartized format for the input data | Marina | 6:00 | 2018-03-16 | 2018-03-29
13 | Create sample files with sample data | Emil | 6:00 | 2018-03-16 | 2018-03-29
14 | Sample GUI Version 1 | Marina | 6:00 | 2018-03-16 | 2018-03-29
15 | Create line chart | Vasil | 6:00 | 2018-03-16 | 2018-03-29
16 | Create bar chart | Vasil | 6:00 | 2018-03-16 | 2018-03-29
17 | Create pie chart | Ivelin | 6:00 | 2018-03-16 | 2018-03-29
18 | Import a map in the project | Lyubomir | 6:00 | 2018-03-16 | 2018-03-29
19 | Adding fuctionality for rescaling | Lyubomir | 5:00 | 2018-03-16 | 2018-03-29
20 | WPF Project prepartion | Joseph | 6:00 | 2018-03-16 | 2018-03-29
21 | Merging code process and master lock | Lyubomir | 1:00 | 2018-03-16 | 2018-03-30
22 | Debug and Test Report | Ivelin & Vasil | 2:00 | 2018-03-23 | 2018-03-30
23 | Update Work Division Report | Joseph & Emil | 2:00 | 2018-03-23 | 2018-03-30
24 | Proof of concept | Marina & Lyubomir | 2:00 | 2018-03-23 | 2018-03-30
25 | Final version of plan for iteration 2 | Team | 6:00 | 2018-03-23 | 2018-03-30

## Iteration 2
Work Devision Report - Iteration 2
Task Nr | Task Description | Assigned Team member | Hours dedicated | Task Start Date | Task Deadline
1 | Application structuring - discussion | Team | 4:00 | 2018-03-09 | 2018-03-16
2 | Update URS | Ivelin & Vasil | 4:00 | 2018-03-09 | 2018-03-16
3 | Concept version of design document | Marina | 4:00 | 2018-03-09 | 2018-03-16
4 | Test Plan (Report) | Joseph & Emil | 4:00 | 2018-03-09 | 2018-03-16
5 | Reseacrch and Introduction to WPF and CSV | Team | 4:00 | 2018-03-09 | 2018-03-22
6 | Import a CSV file with data | Emil | 4:00 | 2018-03-16 | 2018-03-22
7 | Parse data from the imported file | Joseph | 4:00 | 2018-03-16 | 2018-03-22
8 | Pass the imported data to the pie chart | Ivelin | 4:00 | 2018-03-16 | 2018-03-22
9 | Create standartized format for the input data | Marina | 4:00 | 2018-03-16 | 2018-03-22
10 | Create sample files with sample data | Emil | 4:00 | 2018-03-16 | 2018-03-22
11 | Sample GUI Version 1 | Marina | 4:00 | 2018-03-16 | 2018-03-22
12 | Create line chart | Vasil | 4:00 | 2018-03-16 | 2018-03-22
13 | Create bar chart | Vasil | 4:00 | 2018-03-16 | 2018-03-22
14 | Create pie chart | Ivelin | 4:00 | 2018-03-16 | 2018-03-22
15 | Import a map in the project | Lyubomir | 4:00 | 2018-03-16 | 2018-03-22
16 | Adding fuctionality for rescaling | Lyubomir | 4:00 | 2018-03-16 | 2018-03-22
17 | WPF Project prepartion | Joseph | 4:00 | 2018-03-16 | 2018-03-22
18 | Merging code process and master lock | Lyubomir | 4:00 | 2018-03-16 | 2018-03-23

## Iteration 3
Work Devision Report - Iteration 3
Task Nr | Task Description | Assigned Team member | Hours dedicated | Task Start Date | Task Deadline
1 | Application structuring - discussion | Team | 4:00 | 2018-03-09 | 2018-03-16
2 | Update URS | Ivelin & Vasil | 4:00 | 2018-03-09 | 2018-03-16
3 | Concept version of design document | Marina | 4:00 | 2018-03-09 | 2018-03-16
4 | Test Plan (Report) | Joseph & Emil | 4:00 | 2018-03-09 | 2018-03-16
5 | Reseacrch and Introduction to WPF and CSV | Team | 4:00 | 2018-03-09 | 2018-03-22
6 | Import a CSV file with data | Emil | 4:00 | 2018-03-16 | 2018-03-22
7 | Parse data from the imported file | Joseph | 4:00 | 2018-03-16 | 2018-03-22
8 | Pass the imported data to the pie chart | Ivelin | 4:00 | 2018-03-16 | 2018-03-22
9 | Create standartized format for the input data | Marina | 4:00 | 2018-03-16 | 2018-03-22
10 | Create sample files with sample data | Emil | 4:00 | 2018-03-16 | 2018-03-22
11 | Sample GUI Version 1 | Marina | 4:00 | 2018-03-16 | 2018-03-22
12 | Create line chart | Vasil | 4:00 | 2018-03-16 | 2018-03-22
13 | Create bar chart | Vasil | 4:00 | 2018-03-16 | 2018-03-22
14 | Create pie chart | Ivelin | 4:00 | 2018-03-16 | 2018-03-22
15 | Import a map in the project | Lyubomir | 4:00 | 2018-03-16 | 2018-03-22
16 | Adding fuctionality for rescaling | Lyubomir | 4:00 | 2018-03-16 | 2018-03-22
17 | WPF Project prepartion | Joseph | 4:00 | 2018-03-16 | 2018-03-22
18 | Merging code process and master lock | Lyubomir | 4:00 | 2018-03-16 | 2018-03-23